## QnA Log
MART Smart Search — QnA Log (Requirement / Design Clarification)
Arising during the QC process of comparing BRD_AI_Search_VI_v0_0_3_20260812.docx with MART-DE03-Smart_Search_Storyboard-Mobile_App-v0_1-20260816.pptx and attached Figma image — August 17, 2026. Use this QnA-xx code in the 'QnA Ref' / 'Comments' column of the corresponding test case file.
QnA ID | Area / Area | Question/Issue that needs clarification | Reference source (Screen/REQ) | The person stated | Owner needs to respond (Owner) | Status | Impact if not answered | Related Test Cases | Date stated | Answer/Decision (completed by BA) | Response date
QnA-01 | Pre-search — Frequently bought | "Frequently Purchased" block for visitors/non-logged in: HIDE the block completely or REPLACE it with "Best selling at LOTTE Mart"? | SS-SCR-001 (Storyboard, Critical Item #2) | QC (based on Storyboard 'Closing items' #2) | BA / UX | Open | Block Pass/Fail execution for test case SS-SCR-001-SC4-TC2. | SS-SCR-001-SC4-TC2 | 17/08/2026
QnA-02 | Filter panel — Action bar (2 conflicting sources) | PPTX Storyboard (Catch item #3) confirms the Filter Panel IS LACKING the "Clear all"/"Apply (n)" fixed action bar at the bottom of the sheet. But when viewing the real Figma image (Text_Search.png, after brightening — see QnA-16), the Filter sheet has this action bar AVAILABLE ("Reset" + red "Apply"). Which source is correct/newer? | SS-SCR-009 (PPTX storyboard) vs Text_Search.png (ảnh Figma thật) | QC (compare PPTX storyboard with real Figma image) | UX / BA | Open | Test case SS-SCR-009-SC1-TC3 currently executes according to the real Figma image (with action bar) but does not finalize Pass/Fail. | SS-SCR-009-SC1-TC3 | 17/08/2026
QnA-03 | Zero Result — Sub-hint block | The two blocks "Similar keywords" and "You might need?" on Zero Result Page has been designed but is OFF — turn it on in v1 or leave it for the next phase? | SS-SCR-012 (Storyboard, Critical Item #4) | QC (based on Storyboard 'Closing items' #4) | BA / PO | Open | Block Pass/Fail execution for test case SS-SCR-012-SC1-TC3. | SS-SCR-012-SC1-TC3 | 17/08/2026
QnA-04 | Technical Thresholds (Debounce / Fuzzy-match / Confidence) | Technical thresholds that have not yet been specifically set: debounce autocomplete (recommended 300ms — matches BRD NFR-002 but needs TD to confirm actual implementation), fuzzy-match spelling correction threshold (Levenshtein / unaccented Vietnamese phonetic), image recognition confidence threshold. | SS-SCR-002 / SS-SCR-003 / SS-SCR-015 (Storyboard, Key item #5) | QC (based on Storyboard 'Closing items' #5) | TD | Open | Block quantitative Pass/Fail execution for test case SS-SCR-015-SC1-TC3. | SS-SCR-015-SC1-TC3 | 17/08/2026
QnA-05 | Voice Search — Auto-stop threshold | Inconsistency in the storyboard itself: the SS-SCR-017 stage description says "Automatically stops after 6 seconds" (fixed), but "Items to close" #5 says "2 seconds of silence / maximum 15 seconds". Which value is official? | SS-SCR-017 vs Storyboard Closing item #5 | QC (discovered when comparing internal storyboards) | TD / BA | Open | Block quantitative Pass/Fail execution for test case SS-SCR-017-SC1-TC2. | SS-SCR-017-SC1-TC2 | 17/08/2026
QnA-06 | Filter when changing keywords | When a customer changes to a new search keyword, does the system KEEP the current filter in place or AUTOMATICALLY DELETE? | SS-SCR-010 (Storyboard, Critical Item #6) | QC (based on Storyboard 'Closing items' #6) | BA | Open | Impact on future test case design for mid-stream keyword change (no separate TC in this version). |  | 17/08/2026
QnA-07 | Sponsored product placement | Sponsored product insertion position in results grid: FIXED SLOT or Retail Media AUCTION? | SS-SCR-005 (Storyboard, Key Item #7) | QC (based on Storyboard 'Closing items' #7) | PO / Retail Media | Open | Blocked determination of specific expected position in test case SS-SCR-005-SC2-TC2 (only out-of-stock rule can be checked, exact insertion position cannot be checked). | SS-SCR-005-SC2-TC1, SS-SCR-005-SC2-TC2 | 17/08/2026
QnA-08 | Toast Add Cart — CTA | Button on Toast "Added to cart": keep the label "Close" or change it to "View cart" to shorten the path to checkout? | SS-SCR-011 (Storyboard, Key Item #8) | QC (based on Storyboard 'Closing items' #8) | UX | Open | Does not affect current test cases (toast content tested according to wireframe version); New TC needs to be added if button labels are changed. |  | 17/08/2026
QnA-09 | Compare REQ ID codes (Storyboard vs BRD v0.0.3) | Many REQ ID codes in the Storyboard (FR-SP-03, FR-PR-03, FR-SF-02/03, FR-AC-01, FR-IS-01..04, FR-VS-01..03) were SELF-ASSIGNED by the storyboard author himself because the previous BRD version (v0.0.2) did not have codes for these screens. BRD v0.0.3 (current version) has published its own FR-AC/FR-IS/FR-VS code set but the scope may vary. It is necessary to review the entire Screen ID ↔ FR ID mapping before using it as an official tracing key. | Storyboard slide 26 (Closing item #1) + all 19 screen slides | QC (compare BRD v0.0.3 with Storyboard v0.1) | BA | Open | Impact on the reliability of the REQ ID column on the entire Test Scenarios/Test Cases sheet of this test case set - used the code according to the current storyboard, needs to be updated after review by BA. | All rows | 17/08/2026
QnA-10 | Add to Cart — Missing official FR ID | SS-SCR-011 (Add to Cart) is assigned the storyboard REQ ID "FR-AC-01", but FR-AC-01 in BRD v0.0.3 is a spell-correcting banner — unrelated to add-to-cart. BRD currently does not have a separate FR ID for the add cart behavior on the results page. Request BA to issue an official FR ID code. | SS-SCR-011 header vs BRD §5.2 FR-AC-01 | QC (compare BRD v0.0.3) | BA | Open | The REQ ID column of all scenarios/TCs in screen SS-SCR-011 is temporarily left blank/note, waiting for the official code. | SS-SCR-011-SC1-TC1..TC3 | 17/08/2026
QnA-11 | Loading Screen — NFR ID does not exist in BRD | SS-SCR-004 (Loading) is assigned storyboard REQ ID "NFR-SS-01" — this code is NOT in the NFR-001..014 list of BRD v0.0.3. Which NFR actually applies to the Loading visibility threshold (>300ms) and network error fallback (>5s)? | SS-SCR-004 header vs BRD §7 Non-Functional Requirements | QC (compare BRD v0.0.3 §7) | BA / TD | Open | The REQ ID column of test case SS-SCR-004-SC1-TC1 is temporarily noted waiting for confirmation. | SS-SCR-004-SC1-TC1 | 17/08/2026
QnA-12 | Camera Capture — Centering guide frame | Camera Screen currently does not have a frame/overlay to guide customers in placing the product in the center of the frame to increase recognition rate — will it be added in v1? | SS-SCR-013 (Notes/Open Issue) | QC (based on note SS-SCR-013) | UX | Open | Test case SS-SCR-013-SC1-TC3 did not score Fail for this shortcoming in version v0.1, waiting for scope decision. | SS-SCR-013-SC1-TC3 | 17/08/2026
QnA-13 | Sai lệch Screen ID — Toast Add-to-Cart | The slides describing SS-SCR-001 (item 7), SS-SCR-005 (item 6), and SS-SCR-006 (item 5) all cite Toast adding basket as "(SS-SCR-010)", but SS-SCR-010 is actually the "After Applying Filter" screen. Toast extra basket actually belongs to SS-SCR-011. Recommend BA/UX to correct the reference in the storyboard before handing over the dev. | SS-SCR-001/005/006 vs SS-SCR-010/011 | QC (discovered when comparing internal storyboards) | BA / UX | Open | Does not block test case execution (correctly deduced SS-SCR-011 when compiling); just update the original storyboard document. | SS-SCR-011-SC1-TC1 | 17/08/2026
QnA-14 | SS-SCR-007 does not exist in export v0.1 | SS-SCR-005 (item 2) and SS-SCR-015 (item 3) both navigate to "SS-SCR-007", but storyboard v0.1 has no slides/mockups for SS-SCR-007 (the slide set jumps straight from SS-SCR-006 to SS-SCR-008). Missing when exported or merged into SS-SCR-008 (Sort sheet)? | SS-SCR-005 mục 2, SS-SCR-015 mục 3 | QC (compare navigation between slides) | UX | Open | Test case SS-SCR-005-SC1-TC1 temporarily consider SS-SCR-007 = equivalent to SS-SCR-008 (Sort sheet) to be able to execute; Need BA/UX to reconfirm. | SS-SCR-005-SC1-TC1 | 17/08/2026
QnA-15 | List of 8 Sorting options — difference between BRD and Storyboard | BRD FR-PR-06 lists "Most relevant" + 7 old options (Top selling, Most discounted, Highest rated, Price low→high, Price high→low, Name A-Z — only 6 items, not enough 7 as BRD states "8 options"); While SS-SCR-008 lists all 8 items but has an additional "Most-viewed" that BRD does not mention. What is the official 8-item list? | BRD §5.2 FR-PR-06 vs SS-SCR-008 | QC (compare BRD §5.2 FR-PR-06 with SS-SCR-008) | BA | Open | Test case SS-SCR-008-SC1-TC2 does not execute Pass/Fail until there is an official list. | SS-SCR-008-SC1-TC2 | 17/08/2026
QnA-16 | The exported Text_Search.png image file is too dark | The output Text_Search.png is very dark (~98% of the pixels are almost black on the 1568×672 frame) when viewed directly — NOT a corrupted file: after QC brighten/auto-contrast, the entire content is visible (Pre-search → Autocomplete → Correct spelling → Results → Filter → Zero Result → Add basket) and was used to compare the test case (discovered more). QnA-17, QnA-18). We recommend that BA re-export at the correct exposure level from Figma so that normal image viewing tools (not automatically brightened) can read it. | Text_Search.png (project attachment) — processed with PIL autocontrast for comparison | QC (check the attached file, self-corrected for comparison) | BA | Open | No longer blocks comparison (QC fixed it themselves for this review), but it is recommended to re-export the original file with the correct brightness so that other stakeholders (Dev, PM) can view it directly without needing to process the image. | N/A | 17/08/2026
QnA-18 | Filter panel — action bar: PPTX says MISSING, real Figma shows YES | See QnA-02 for details — here's the full technical write-up: The PPTX storyboard (Catch item #3) records the fixed action bar at the bottom of the Filter Panel as a DESIGN GAP (missing). Image Text_Search.png (real Figma, after brightening) shows that this bar ALREADY EXISTS with 2 "Reset" / "Apply" buttons. Possibility that the PPTX storyboard is built from a version of Figma that is older than the later export image — BA needs to confirm which Figma version is the latest/official version before finalizing the entire document. | SS-SCR-009 (PPTX) vs Text_Search.png (Figma thật) | QC (compare PPTX storyboard with real Figma image, discover when reviewing as required) | BA / UX | Open | Impact on the overall reliability of the entire PPTX storyboard if it is not synchronized with the latest Figma version — request BA to compare the whole thing, not just the Filter screen. | SS-SCR-009-SC1-TC3 | 17/08/2026
QnA-19 | Switch search method midway | When a visitor is viewing Text Search results (with filter/sort applied) and then switches to Image or Voice Search, is the old filter/sort retained for the new results or automatically reset? BRD/Storyboard does not describe the case of SWITCHING METHODS (only QnA-06 talks about changing keywords with the SAME method). | SS-SCR-005 (cross-screen inference) | QC (additional review according to 2nd review request) | BA / UX | Open | Test case SS-SCR-005-SC5-TC1 does not mark Pass/Fail until confirmed. | SS-SCR-005-SC5-TC1 | 17/08/2026
QnA-20 | Login session expired mid-search | If a Member's login session expires while in the middle of an operation (eg: viewing personalized results, or adding a shopping cart), how does the UI handle it (force a login again immediately, or continue in Guest mode)? There are no regulatory documents yet. | Not included in BRD/Storyboard — QC automatically detects when reviewing for completeness | QC (additional review) | BA / TD | Open | There are no specific test cases in this set because there is a lack of specification to write detailed test steps; Recorded as input for the next update. | N/A — need to add TC after specification | 17/08/2026
QnA-21 | Toast Add-to-cart when operations are intensive | When a customer clicks (+) continuously on the same product or many different products in a short time, Toast confirms whether the queue is displayed one after another, or is there only one Toast continuously updated/replaced? Not yet described in Storyboard. | SS-SCR-011 (inferred from common UX patterns, not documented) | QC (additional review) | UX | Open | Test cases SS-SCR-011-SC2-TC1 (spam + button) and SS-SCR-011-SC3-TC1 (2 consecutive SKUs) do not score Pass/Fail according to specific Toast behavior until confirmed. | SS-SCR-011-SC2-TC1, SS-SCR-011-SC3-TC1 | 17/08/2026
QnA-22 | Voice Search — handles counts & units | How to handle counts and units in sentences (e.g. "two liters", "500 grams") before entering the search query — the storyboard itself notes this as a "need to fix" point but no decision has been made yet. | SS-SCR-017 (Notes/Open Issue, PPTX storyboard) | QC (excerpt from original Storyboard notes SS-SCR-017) | TD / BA | Open | Test case SS-SCR-017-SC2-TC1 does not score Pass/Fail according to specific handling until a decision is made. | SS-SCR-017-SC2-TC1 | 17/08/2026
QnA-23 | Navigate when tapping suggested products on Zero Result Page | When a customer taps on a Substitute/Cross-sell product on the Zero Result Page, does the system open that product's PDP page directly, or run a new search query by product name? Storyboard does not clearly describe this navigation behavior. | SS-SCR-012 (inference, no specific navigation description in storyboard) | QC (additional review) | BA / UX | Open | Test case SS-SCR-012-SC3-TC1 does not score Pass/Fail on the specific navigation destination until confirmed. | SS-SCR-012-SC3-TC1 | 17/08/2026
QnA-24 | Revoke Camera permissions mid-session | When Camera permission is revoked in System Settings WHILE the app is running (different from denying the first permission request with a test case), how does the Camera Screen UI handle when returning to the foreground? | SS-SCR-013 (inference, beyond the scope of the original storyboard description) | QC (additional review) | TD / UX | Open | Test case SS-SCR-013-SC3-TC1 does not mark Pass/Fail until confirmed. | SS-SCR-013-SC3-TC1 | 17/08/2026
QnA-25 | Cart badge format when exceeding 2 digits | When the number of products in the cart exceeds 99, does the badge on the Shopping Cart icon display the shortened form ("99+") or the full number? There are no regulations in BRD/Storyboard. | Global Header (BRD §6.1) — no large number format specified | QC (additional review) | UX | Open | Test case SS-SCR-001-SC1-TC2 does not score Pass/Fail according to the specific format until confirmed. | SS-SCR-001-SC1-TC2 | 17/08/2026
QnA-26 | Network error when loading Pre-search (before search) | When the network connection is lost at the moment of opening the Pre-search Screen (before the visitor performs any searches), how does the UI handle Trending/Regular blocks (skeleton loading, local error messages by block, or block hiding)? Different from network error during search processing, which is clearly specified in SS-SCR-004 (>5s → network error + Retry). | SS-SCR-001 (inferred, beyond original description scope) | QC (additional review) | UX / TD | Open | Test case SS-SCR-001-SC5-TC1 does not mark Pass/Fail until confirmed. | SS-SCR-001-SC5-TC1 | 17/08/2026
QnA-27 | Pre-search — Recent Searches (multi-device sync) | When a Member is logged into the same account on 2+ devices, and clears Recent Searches ("Clear all") on Device A only, does Device B's own locally-cached Recent Searches get cleared too (server-side sync), or does it keep showing its own separately-cached history until the shopper searches again on Device B? BRD/Storyboard doesn't specify whether Recent Searches is purely client-local or synced server-side per account. | SS-SCR-001 (inferred, cross-device behavior not covered by storyboard) | QC (additional review) | BA / TD | Open | Test case SS-SCR-001-SC2-TC3 does not mark Pass/Fail on the specific cross-device sync expectation until confirmed. | SS-SCR-001-SC2-TC3 | 18/08/2026
QnA-28 | Pre-search — Frequently Purchased (Member with empty order history) | For a logged-in Member who has NEVER had a completed order (empty order history — different from a Guest, already covered by QnA-01), does the "Frequently Purchased" block get hidden entirely, replaced with "Best-sellers at LOTTE Mart" (same fallback proposed for Guests), or something else? BRD/Storyboard doesn't cover this specific case. | SS-SCR-001 (inferred, not covered by storyboard — distinct from the Guest case) | QC (additional review) | BA / UX | Open | Test case SS-SCR-001-SC4-TC4 does not mark Pass/Fail until confirmed. | SS-SCR-001-SC4-TC4 | 18/08/2026
QnA-29 | Frequently Purchased — order-history lookback window (2 conflicting sources) | The Storyboard specifies a fixed T=90-day lookback window for which COMPLETED orders count toward "Frequently Purchased". The BRD instead describes an adaptive window: successfully-delivered orders within the most recent 3-6 months — starting at 3 months, then expanding +1 month at a time if that month and the ones after it have no order history, up to a maximum lookback of 6 months. These are two different mechanisms (fixed 90-day cutoff vs. an adaptive 3-6 month expanding window), not just a unit-conversion difference. Which source is authoritative? | SS-SCR-001-SC4 (Storyboard, "COMPLETED orders in the last 90 days") vs BRD (adaptive 3-6 month expanding window) | QC (compare Storyboard precondition with BRD wording) | BA / TD | Open | Blocks a specific Pass/Fail determination for the order-recency test cases in SS-SCR-001-SC4 (SC4-TC1, SC4-TC3) until the official window logic is confirmed. | SS-SCR-001-SC4-TC1, SS-SCR-001-SC4-TC3 | 18/08/2026
Total QnA:
Open:
Answered (Resolved):